## RTM
Requirements Traceability Matrix — LendingClub Credit Decisioning & Portfolio Insights
Full chain: BR -> FR -> Story (Jira VEL) -> Test Case -> Status. CR-001 row highlighted. Author: Deepak Nepram.
BR ID | Business requirement (abridged) | MoSCoW | FR ID(s) | Story (US / VEL) | Test case(s) | Delivery status | Notes
BR-01 | Single reproducible cleaned dataset from both raw files | Must | FR-001, FR-002, FR-003, FR-005 | US-01/VEL-4, US-02/VEL-5, US-03/VEL-6, US-04/VEL-7 | TC-01, TC-02 | Delivered (Sprint 1) | prepare_data.py, seed 42
BR-02 | Governed KPI definitions to stop definitional drift | Must | FR-007 | US-06/VEL-9 | TC-12 | Delivered (Sprint 1) | kpi-dictionary.md; resolved-basis charge-off
BR-03 | Visible data-quality reporting on every pipeline run | Must | FR-006 | US-05/VEL-8 | TC-10 | Delivered (Sprint 1) | cleaning-report.txt auto-written
BR-04 | Documented, defensible credit-review rules | Must | FR-008, FR-009 | US-07/VEL-10, US-08/VEL-11 | TC-11 | Delivered (Sprint 2) | RULE-01..06 with Day-9 evidence
BR-05 | Forecastable manual-review workload | Should | FR-009, FR-010 | US-08/VEL-11, US-10/VEL-13 | TC-11 | Delivered (Sprint 2) | 6.77% of funded book flagged
BR-06 | Evidence-based threshold setting (Credit vs Ops resolution) | Should | FR-012, FR-017 | US-09/VEL-12, US-13/VEL-16 | TC-06 | Partially delivered | US-09 deferred via CR-001 absorb; evidence later closed by Day-9 run
BR-07 | Executive at-a-glance portfolio view | Must | FR-014, FR-015 | US-11/VEL-14, US-12/VEL-15 | TC-03, TC-04 | Delivered (Sprints 1-2) | Tab 1 BANs + trend
BR-08 | Risk drill-down by grade, term, vintage, purpose | Must | FR-016 | US-12/VEL-15 | TC-05 | Delivered (Sprint 2) | Tab 3 heatmap/vintage/scatter
BR-09 | Policy validation view (accepted vs rejected) | Should | FR-017 | US-13/VEL-16 | TC-06 | Delivered (Sprint 2) | DTI basis (Risk_Score 66.9% null)
BR-10 | Self-serve filtering, <=3 clicks, public access | Must | FR-018, FR-019, FR-020 | US-14/VEL-17, US-15/VEL-18 | TC-08, TC-09 | Delivered (Sprint 2) | Tableau Public link, 4 global filters
BR-11 | Geographic concentration reporting (state level) | Must | FR-021 | US-16/VEL-19 | TC-07 | Delivered (Sprint 2 via CR-001) | Absorbed mid-sprint; US-09 deferred to protect goal
Coverage checks
Every BR maps to >=1 FR | Yes - 11/11
Every FR maps to >=1 story | Yes - FR-001..FR-021 across US-01..US-16 (VEL-4..VEL-19)
Every Must BR has >=1 passing test | Yes - see UAT workbook
Change control traced end-to-end | CR-001 -> BR-11 -> FR-021 -> US-16/VEL-19 -> TC-07
Orphan requirements (built without BR) | None